## JANUARY
EXTERNAL LOANS IN EXECUTION AS OF 01/31/2025
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant Program | 2019-04-05 | 6492 | 2020-01-02 | 2028-05-07 | 3.2658 | 125000000 | 31030658.3 | 24.82% | 93969341.7
MAG | Project to Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2025-05-25 | 4 meses | 15000000 | 12681077.45 | 84.54% | 2318922.55
MEC | Project to Support Extended School Days and Improved Transportation Conditions for Students Attending Rural Official Schools | 2016-04-09 | 5961 | 2017-10-31 | 2025-06-10 | 5 meses | 20000000 | 17341809.5 | 86.71% | 2658190.5
MEF | Investments in Public Finances for Sustainable Development Project | 2019-04-05 | 6693 | 2021-01-14 | 2027-01-19 | 1.9671 | 25000000 | 11003461.79 | 44.01% | 13996538.21
MIC | Support for Business Development Services to Paraguayan Exporting Companies Program | 2017-07-18 | 6218 | 2018-11-19 | 2025-11-23 | 0.81096 | 10000000 | 7234067 | 72.34% | 2765933
MOPC | Rural Road Improvement Program II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0.96164 | 62000000 | 57264818.98 | 92.36% | 4735181.02
MOPC | Upgrade and Maintenance Project for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-20 | 0.63562 | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance Program | 2017-07-08 | 6236 | 2018-11-23 | 2025-11-30 | 0.83014 | 90000000 | 67124059.58 | 74.58% | 22875940.42
MOPC | Housing and Rehabilitation Program for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 2.7836 | 100000000 | 5181276.25 | 5.181% | 94818723.75
SENACSA | Project to Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 1.6548 | 15000000 | 8062759.83 | 53.75% | 6937240.17
SENASA | Water and Sanitation System Construction Project for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-29 | 0.57534 | 40000000 | 34884660.34 | 87.21% | 5115339.66
MITIC | Digital Agenda Support Program | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 3.2685 | 130000000 | 38973629.44 | 29.98% | 91026370.56
MUVH | Improvement of Housing and Habitat Program | 2015-11-02 | 5665 | 2016-10-14 | 2025-10-20 | 0.71781 | 30000000 | 27331800.45 | 91.11% | 2668199.55
INE | Program to Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 1.8877 | 43000000 | 34712242.02 | 80.73% | 8287757.98
MOPC | Program to Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 2.8959 | 235000000 | 195198299.44 | 83.06% | 39801700.56
MOPC | Program to improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-03-16 | 4.1233 | 215000000 | 79284843.58 | 36.88% | 135715156.42
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay Program | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 2.6164 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 3.2548 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 3.8137 | 30000000 | 8975310.13 | 29.92% | 21024689.87
MOPC | Potable Water and Sanitation Project for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 4.2795 | 115000000 | 0 | 0% | 115000000
MSPBS | Program to Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 4.2301 | 45000000 | 563598.16 | 1.252% | 44436401.84
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-24 | 4.2301 | 105000000 | 0 | 0% | 105000000
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector Program | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 3.4027 | 30000000 | 5015629 | 16.72% | 24984371
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions Project | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.6247 | 70000000 | 39741857.8 | 56.77% | 30258142.2
MOPC | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 5.2055 | 34050000 | 0 | 0% | 34050000
MSPBS | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 5.2055 | 25950000 | 0 | 0% | 25950000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3.989 | 260000000 | 0 | 0% | 260000000
| TOTAL IADB | [5 empty] | 2070000000 | 845178079.11 | 40.83% | 1224821920.89
MAG | Market Access for Agricultural Products Project | 2020-04-14 | 6524 | 2020-03-26 | 2026-06-30 | 1.411 | 100000000 | 55448917.71 | 55.45% | 44551082.29
MSPBS | Paraguay Public Health Sector Strengthening Program | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 1.411 | 115000000 | 76450369.27 | 66.48% | 38549630.73
MOPC | Transport Connectivity Project – Habilitación de la Red Pavimentada | 2016-09-13 | 6025 | 2018-01-05 | 2025-12-31 | 0.91507 | 100000000 | 72668186.3 | 72.67% | 27331813.7
MOPC | Asuncion Riverfront Urban Resilience Project | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 3.9123 | 105000000 | 4552794.75 | 4.336% | 100447205.25
MOPC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2029-01-07 | 3.937 | 104190000 | 0 | 0% | 104190000
MEC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2029-01-07 | 3.937 | 21110000 | 0 | 0% | 21110000
| TOTAL IBRD | [5 empty] | 545300000 | 209120268.03 | 38.35% | 336179731.97
ANDE | Metropolitan Area Distribution System Improvement and National Interconnected System Reinforcement Project | 2017-01-20 | 6023 | 2018-01-05 | 2025-07-16 | 6 meses | 150000000 | 147301129.81 | 98.2% | 2698870.19
ANDE | Improvement Project for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2024-06-12 | - | 150000000 | 125921741.74 | 83.95% | 24078258.26
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening Program | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0.97808 | 170000000 | 151965758.61 | 89.39% | 18034241.39
MOPC | Rural Roads and Bridges Improvement Project in the Eastern Region | 2017-08-18 | 6237 | 2018-12-03 | 2025-06-05 | 5 meses | 100000000 | 87251356.81 | 87.25% | 12748643.19
MOPC | Paved Road Rehabilitation and Maintenance Program - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 0.8274 | 100000000 | 76214304.21 | 76.21% | 23785695.79
MOPC | Integration Corridor Improvement and Road Reconstruction Program | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 5 meses | 222076000 | 201890774.09 | 90.91% | 20185225.91
MOPC | Project for the development and maintenance of National Route No. 9 and access roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-19 | 0.63288 | 400000000 | 394388522.9 | 98.6% | 5611477.1
MOPC | Enabling the Paved Road Network Program | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | - | 100000000 | 91970505.89 | 91.97% | 8029494.11
MOPC | Project for the Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 0.89589 | 212000000 | 113332784.64 | 53.46% | 98667215.36
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization Program of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-17 | 1.8767 | 250000000 | 87431179.85 | 34.97% | 162568820.15
MOPC | Construction Project for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2030-04-05 | 5.1781 | 100000000 | 22640999.73 | 22.64% | 77359000.27
MOPC | Sanitation in Intermediate Cities Program | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 3.4411 | 52292000 | 2670692.33 | 5.107% | 49621307.67
MOPC | Sanitation Works Program for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 3.7315 | 160000000 | 1410000 | 0.8812% | 158590000
ANDE | Paraguay's Electricity Sector Development Support Program (SWAP) | 2024-10-18 | 7415 | 2024-12-18 | 2026-12-18 | 1.8795 | 120000000 | 120000000 | 100% | 0
| TOTAL CAF | [5 empty] | 2286368000 | 1624389750.61 | 71.05% | 661978249.39
MOPC | Paved Road Rehabilitation and Maintenance Program - PAR 24 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 0.87123 | 42857143 | 36619928.88 | 85.45% | 6237214.12
MOPC | Rural Roads and Bridges Improvement Project in the Eastern Region - PAR 23 | 2017-08-28 | 6237 | 2018-12-03 | 2024-12-14 | - | 42911000 | 42911000 | 100% | 0
MOPC | Enabling the Paved Road Network Program | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 1.0329 | 42750000 | 36695088.58 | 85.84% | 6054911.42
ANDE | Construction: Transformer substation and power transmission lines in Valenzuela, Cordillera Department | 2019-05-21 | 6493 | 2020-01-02 | 2025-06-30 | 5 meses | 70000000 | 69999999.9 | 100% | 0.1
MOPC | Improvement and Paving Project for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-11 | 4.1945 | 354245764 | 52236075.52 | 14.75% | 302009688.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 3.4521 | 220000000 | 11313580 | 5.143% | 208686420
ANDE | Construction project for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-27 | 2.6548 | 45000000 | 0 | 0% | 45000000
| TOTAL FONPLATA | [5 empty] | 817763907 | 249775672.88 | 30.54% | 567988234.12
MAG | Project for Improved Family and Indigenous Production in Northeast Paraguay (PROMAFI) | 2016-10-06 | 6215 | 2018-10-31 | 2025-06-30 | 5 meses | 16379860 | 8525804.6369 | 52.05% | 7854055.3631
| TOTAL IFAD | [5 empty] | 16379860 | 8525804.6369 | 52.05% | 7854055.3631
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 0.91507 | 21600000 | 20991518.11 | 97.18% | 608481.89
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 0.91507 | 10400000 | 2597669.75 | 24.98% | 7802330.25
MOPC | South-West Integration Road Corridors Infrastructure Programe | 2015-10-11 | 5600 | 2016-05-16 | 2024-06-30 | - | 43364000 | 43364000 | 100% | 0
| TOTAL OFID | [5 empty] | 75364000 | 61652607.94 | 81.81% | 13711392.06
ANDE | ANDE Transmission & Distribution System Upgrade (PHASE II) | 2017-12-06 | 6143 | 2018-08-07 | 2027-12-13 | 2.8658 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL EIB | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5905175767 | 3064705298.6969 | 51.9% | 2840470468.3031
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
SENASA | Potable Water and Sanitation Program for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-19 | 0.54795 | 20000000 | 16056241.61 | 80.28% | 3943758.39
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 2029-04-24 | 4.2301 | 60000000 | 207510 | 0.3459% | 59792490
| TOTAL ICO | [5 empty] | 80000000 | 16263751.61 | 20.33% | 63736248.39
MOPC | Project for Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 4.2795 | 59036534.1093 | 0 | 0% | 59036534.1093
ANDE | Project for Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.6247 | 60096993.2105 | 30415376.4152 | 50.61% | 29681616.7953
| TOTAL JICA | [5 empty] | 119133527.3198 | 30415376.4152 | 25.53% | 88718150.9046
ANDE | Construction Project of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2025-09-15 | 0.62192 | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0 | 75000000
ANDE | The High-Voltage Transmission System Expansion Project (Paraguay) | 2023-01-26 | 7414 | 2023-09-15 | 2029-01-26 | 3.989 | 30000000 | 0 | 0% | 30000000
| TOTAL ICDF | [5 empty] | 30000000 | 0 | 0% | 30000000
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 304133527.3198 | 46679128.0252 | 15.35% | 257454399.2946
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 6209309294.3198 | 3111384426.722 | 50.11% | 3097924867.5977
*Update of disbursements made from the year 2010 to 01/31/2025, according to SIGADE report 02/25/2025, 09:00 AM. - Exchange Rate: 01/31/2025 - Preliminary figures, subject to revision

## FEBRUARY
EXTERNAL LOANS IN EXECUTION AS OF 02/28/2025
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant Program | 2019-04-05 | 6492 | 2020-01-02 | 2028-05-07 | 3.189 | 125000000 | 31030658.3 | 24.82% | 93969341.7
MAG | Project to Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2025-05-25 | 3 meses | 15000000 | 12879090.95 | 85.86% | 2120909.05
MEC | Project to Support Extended School Days and Improved Transportation Conditions for Students Attending Rural Official Schools | 2016-04-09 | 5961 | 2017-10-31 | 2025-06-10 | 4 meses | 20000000 | 17341809.5 | 86.71% | 2658190.5
MEF | Investments in Public Finances for Sustainable Development Project | 2019-04-05 | 6693 | 2021-01-14 | 2027-01-19 | 1.8904 | 25000000 | 11003461.79 | 44.01% | 13996538.21
MIC | Support for Business Development Services to Paraguayan Exporting Companies Program | 2017-07-18 | 6218 | 2018-11-19 | 2025-11-23 | 0.73425 | 10000000 | 7234067 | 72.34% | 2765933
MOPC | Rural Road Improvement Program II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0.88493 | 62000000 | 57264818.98 | 92.36% | 4735181.02
MOPC | Upgrade and Maintenance Project for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-20 | 0.5589 | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance Program | 2017-07-08 | 6236 | 2018-11-23 | 2025-11-30 | 0.75342 | 90000000 | 67124059.58 | 74.58% | 22875940.42
MOPC | Housing and Rehabilitation Program for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 2.7068 | 100000000 | 10782632.34 | 10.78% | 89217367.66
SENACSA | Project to Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 1.5781 | 15000000 | 8062759.83 | 53.75% | 6937240.17
SENASA | Water and Sanitation System Construction Project for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-29 | 6 meses | 40000000 | 34884660.34 | 87.21% | 5115339.66
MITIC | Digital Agenda Support Program | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 3.1918 | 130000000 | 38973629.44 | 29.98% | 91026370.56
MUVH | Improvement of Housing and Habitat Program | 2015-11-02 | 5665 | 2016-10-14 | 2025-10-20 | 0.6411 | 30000000 | 27331800.45 | 91.11% | 2668199.55
INE | Program to Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 1.811 | 43000000 | 34712242.02 | 80.73% | 8287757.98
MOPC | Program to Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 2.8192 | 235000000 | 195198299.44 | 83.06% | 39801700.56
MOPC | Program to improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-03-16 | 4.0466 | 215000000 | 79284843.58 | 36.88% | 135715156.42
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay Program | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 2.5397 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 3.1781 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 3.737 | 30000000 | 8975310.13 | 29.92% | 21024689.87
MOPC | Potable Water and Sanitation Project for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 4.2027 | 115000000 | 0 | 0% | 115000000
MSPBS | Program to Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 4.1534 | 45000000 | 563598.16 | 1.252% | 44436401.84
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-24 | 4.1534 | 105000000 | 0 | 0% | 105000000
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector Program | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 3.326 | 30000000 | 5015629 | 16.72% | 24984371
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions Project | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.5479 | 70000000 | 39741857.8 | 56.77% | 30258142.2
MOPC | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 5.1288 | 34050000 | 0 | 0% | 34050000
MSPBS | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 5.1288 | 25950000 | 0 | 0% | 25950000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3.9123 | 260000000 | 0 | 0% | 260000000
| TOTAL IADB | [5 empty] | 2070000000 | 850977448.7 | 41.11% | 1219022551.3
MAG | Market Access for Agricultural Products Project | 2020-04-14 | 6524 | 2020-03-26 | 2026-06-30 | 1.3342 | 100000000 | 55448917.71 | 55.45% | 44551082.29
MSPBS | Paraguay Public Health Sector Strengthening Program | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 1.3342 | 115000000 | 76450369.27 | 66.48% | 38549630.73
MOPC | Transport Connectivity Project – Habilitación de la Red Pavimentada | 2016-09-13 | 6025 | 2018-01-05 | 2025-12-31 | 0.83836 | 100000000 | 72668186.3 | 72.67% | 27331813.7
MOPC | Asuncion Riverfront Urban Resilience Project | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 3.8356 | 105000000 | 4552794.75 | 4.336% | 100447205.25
MOPC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2029-01-07 | 3.8603 | 104190000 | 0 | 0% | 104190000
MEC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2029-01-07 | 3.8603 | 21110000 | 0 | 0% | 21110000
| TOTAL IBRD | [5 empty] | 545300000 | 209120268.03 | 38.35% | 336179731.97
ANDE | Metropolitan Area Distribution System Improvement and National Interconnected System Reinforcement Project | 2017-01-20 | 6023 | 2018-01-05 | 2025-07-16 | 5 meses | 150000000 | 148801129.81 | 99.2% | 1198870.19
ANDE | Improvement Project for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2026-12-12 | - | 150000000 | 130921741.74 | 87.28% | 19078258.26
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening Program | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0.90137 | 170000000 | 157965758.61 | 92.92% | 12034241.39
MOPC | Rural Roads and Bridges Improvement Project in the Eastern Region | 2017-08-18 | 6237 | 2018-12-03 | 2025-06-05 | 4 meses | 100000000 | 87251356.81 | 87.25% | 12748643.19
MOPC | Paved Road Rehabilitation and Maintenance Program - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 0.75068 | 100000000 | 80270580.95 | 80.27% | 19729419.05
MOPC | Integration Corridor Improvement and Road Reconstruction Program | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 4 meses | 222076000 | 201890774.09 | 90.91% | 20185225.91
MOPC | Project for the development and maintenance of National Route No. 9 and access roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-19 | 0.55616 | 400000000 | 394388522.9 | 98.6% | 5611477.1
MOPC | Enabling the Paved Road Network Program | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | 1.8822 | 100000000 | 91970505.89 | 91.97% | 8029494.11
MOPC | Project for the Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 0.81918 | 212000000 | 113332784.64 | 53.46% | 98667215.36
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization Program of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-17 | 1.8 | 250000000 | 87431179.85 | 34.97% | 162568820.15
MOPC | Construction Project for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2030-04-05 | 5.1014 | 100000000 | 22640999.73 | 22.64% | 77359000.27
MOPC | Sanitation in Intermediate Cities Program | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 3.3644 | 52292000 | 2670692.33 | 5.107% | 49621307.67
MOPC | Sanitation Works Program for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 3.6548 | 160000000 | 1410000 | 0.8812% | 158590000
| TOTAL CAF | [5 empty] | 2166368000 | 1520946027.35 | 70.21% | 645421972.65
MOPC | Paved Road Rehabilitation and Maintenance Program - PAR 24 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 0.79452 | 42857143 | 36619928.88 | 85.45% | 6237214.12
MOPC | Enabling the Paved Road Network Program | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 0.95616 | 42750000 | 36695088.58 | 85.84% | 6054911.42
MOPC | Improvement and Paving Project for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-11 | 4.1178 | 354245764 | 52236075.52 | 14.75% | 302009688.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 3.3753 | 220000000 | 27744451 | 12.61% | 192255549
ANDE | Construction project for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-27 | 2.5781 | 45000000 | 0 | 0% | 45000000
| TOTAL FONPLATA | [5 empty] | 704852907 | 153295543.98 | 21.75% | 551557363.02
MAG | Project for Improved Family and Indigenous Production in Northeast Paraguay (PROMAFI) | 2016-10-06 | 6215 | 2018-10-31 | 2025-06-30 | 4 meses | 16450960 | 8525804.6369 | 51.83% | 7925155.3631
| TOTAL IFAD | [5 empty] | 16450960 | 8525804.6369 | 51.83% | 7925155.3631
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 0.83836 | 21600000 | 21180854.87 | 98.06% | 419145.13
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 0.83836 | 10400000 | 4385267.83 | 42.17% | 6014732.17
| TOTAL OFID | [5 empty] | 32000000 | 25566122.7 | 79.89% | 6433877.3
ANDE | ANDE Transmission & Distribution System Upgrade (PHASE II) | 2017-12-06 | 6143 | 2018-08-07 | 2027-12-13 | 2.789 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL EIB | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5628971867 | 2829193750.9669 | 50.26% | 2799778116.0331
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
SENASA | Potable Water and Sanitation Program for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-19 | 6 meses | 20000000 | 16056241.61 | 80.28% | 3943758.39
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 2029-04-24 | 4.1534 | 60000000 | 207510 | 0.3459% | 59792490
| TOTAL ICO | [5 empty] | 80000000 | 16263751.61 | 20.33% | 63736248.39
MOPC | Project for Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 4.2027 | 60600026.5498 | 0 | 0% | 60600026.5498
ANDE | Project for Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.5479 | 61688570.2907 | 30548099.1147 | 49.52% | 31140471.176
| TOTAL JICA | [5 empty] | 122288596.8406 | 30548099.1147 | 24.98% | 91740497.7259
ANDE | Construction Project of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2025-09-15 | 0.54521 | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0 | 75000000
ANDE | The High-Voltage Transmission System Expansion Project (Paraguay) | 2023-01-26 | 7414 | 2023-09-15 | 2029-01-26 | 3.9123 | 30000000 | 0 | 0% | 30000000
| TOTAL ICDF | [5 empty] | 30000000 | 0 | 0% | 30000000
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 307288596.8406 | 46811850.7247 | 15.23% | 260476746.1159
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 5936260463.8406 | 2876005601.6915 | 48.45% | 3060254862.149
*Update of disbursements made from the year 2010 to 01/31/2025, according to SIGADE report 02/25/2025, 09:00 AM. - Exchange Rate: 01/31/2025 - Preliminary figures, subject to revision

## MARCH
EXTERNAL LOANS IN EXECUTION AS OF 03/31/2025
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant Program | 2019-04-05 | 6492 | 2020-01-02 | 2028-05-07 | 3.1041 | 125000000 | 31030658.3 | 24.82% | 93969341.7
MAG | Project to Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2025-05-25 | 2 months | 15000000 | 12879090.95 | 85.86% | 2120909.05
MEC | Project to Support Extended School Days and Improved Transportation Conditions for Students Attending Rural Official Schools | 2016-04-09 | 5961 | 2017-10-31 | 2025-06-10 | 3 months | 20000000 | 17341809.5 | 86.71% | 2658190.5
MEF | Investments in Public Finances for Sustainable Development Project | 2019-04-05 | 6693 | 2021-01-14 | 2027-01-19 | 1.8055 | 25000000 | 13069362.59 | 52.28% | 11930637.41
MIC | Support for Business Development Services to Paraguayan Exporting Companies Program | 2017-07-18 | 6218 | 2018-11-19 | 2025-11-23 | 0.64932 | 10000000 | 9615119.78 | 96.15% | 384880.22
MOPC | Rural Road Improvement Program II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0.8 | 62000000 | 57264818.98 | 92.36% | 4735181.02
MOPC | Upgrade and Maintenance Project for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-20 | 6 months | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance Program | 2017-07-08 | 6236 | 2018-11-23 | 2025-11-30 | 0.66849 | 90000000 | 67124059.58 | 74.58% | 22875940.42
MOPC | Housing and Rehabilitation Program for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 2.6219 | 100000000 | 10782632.34 | 10.78% | 89217367.66
SENACSA | Project to Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 1.4932 | 15000000 | 8062759.83 | 53.75% | 6937240.17
SENASA | Water and Sanitation System Construction Project for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-29 | 5 months | 40000000 | 34884660.34 | 87.21% | 5115339.66
MITIC | Digital Agenda Support Program | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 3.1068 | 130000000 | 38973629.44 | 29.98% | 91026370.56
MUVH | Improvement of Housing and Habitat Program | 2015-11-02 | 5665 | 2016-10-14 | 2025-10-20 | 0.55616 | 30000000 | 27331800.45 | 91.11% | 2668199.55
INE | Program to Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 1.726 | 43000000 | 34712242.02 | 80.73% | 8287757.98
MOPC | Program to Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 2.7342 | 235000000 | 195198299.44 | 83.06% | 39801700.56
MOPC | Program to improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-03-16 | 3.9616 | 215000000 | 79284843.58 | 36.88% | 135715156.42
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay Program | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 2.4548 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 3.0932 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 3.6521 | 30000000 | 8975310.13 | 29.92% | 21024689.87
MOPC | Potable Water and Sanitation Project for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 4.1178 | 115000000 | 0 | 0% | 115000000
MSPBS | Program to Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 4.0685 | 45000000 | 563598.16 | 1.252% | 44436401.84
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-24 | 4.0685 | 105000000 | 0 | 0% | 105000000
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector Program | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 3.2411 | 30000000 | 5015629 | 16.72% | 24984371
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions Project | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.463 | 70000000 | 39741857.8 | 56.77% | 30258142.2
MOPC | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 5.0438 | 34050000 | 0 | 0% | 34050000
MSPBS | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 5.0438 | 25950000 | 0 | 0% | 25950000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3.8274 | 260000000 | 0 | 0% | 260000000
| TOTAL IADB | [5 empty] | 2070000000 | 855424402.28 | 41.32% | 1214575597.72
MAG | Market Access for Agricultural Products Project | 2020-04-14 | 6524 | 2020-03-26 | 2026-06-30 | 1.3342 | 100000000 | 55448917.71 | 55.45% | 44551082.29
MSPBS | Paraguay Public Health Sector Strengthening Program | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 1.3342 | 115000000 | 77935396.98 | 67.77% | 37064603.02
MOPC | Transport Connectivity Project – Habilitación de la Red Pavimentada | 2016-09-13 | 6025 | 2018-01-05 | 2025-12-31 | 9 months | 100000000 | 72668186.3 | 72.67% | 27331813.7
MOPC | Asuncion Riverfront Urban Resilience Project | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 3.8356 | 105000000 | 4552794.75 | 4.336% | 100447205.25
MOPC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2029-01-07 | 3.8603 | 104190000 | 0 | 0% | 104190000
MEC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2029-01-07 | 3.8603 | 21110000 | 0 | 0% | 21110000
| TOTAL IBRD | [5 empty] | 545300000 | 210605295.74 | 38.62% | 334694704.26
ANDE | Metropolitan Area Distribution System Improvement and National Interconnected System Reinforcement Project | 2017-01-20 | 6023 | 2018-01-05 | 2025-07-16 | 4 months | 150000000 | 148801129.81 | 99.2% | 1198870.19
ANDE | Improvement Project for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2026-12-12 | 1.7014 | 150000000 | 130921741.74 | 87.28% | 19078258.26
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening Program | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0.81644 | 170000000 | 157965758.61 | 92.92% | 12034241.39
MOPC | Rural Roads and Bridges Improvement Project in the Eastern Region | 2017-08-18 | 6237 | 2018-12-03 | 2025-06-05 | 3 months | 100000000 | 87251356.81 | 87.25% | 12748643.19
MOPC | Paved Road Rehabilitation and Maintenance Program - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 0.66575 | 100000000 | 80270580.95 | 80.27% | 19729419.05
MOPC | Integration Corridor Improvement and Road Reconstruction Program | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 3 months | 222076000 | 201890774.09 | 90.91% | 20185225.91
MOPC | Project for the development and maintenance of National Route No. 9 and access roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-19 | 6 months | 400000000 | 394388522.9 | 98.6% | 5611477.1
MOPC | Enabling the Paved Road Network Program | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | 1.7973 | 100000000 | 92706138.98 | 92.71% | 7293861.02
MOPC | Project for the Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 0.73425 | 212000000 | 113332784.64 | 53.46% | 98667215.36
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization Program of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-17 | 1.7151 | 250000000 | 93431179.85 | 37.37% | 156568820.15
MOPC | Construction Project for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2030-04-05 | 5.0164 | 100000000 | 22640999.73 | 22.64% | 77359000.27
MOPC | Sanitation in Intermediate Cities Program | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 3.2795 | 52292000 | 2670692.33 | 5.107% | 49621307.67
MOPC | Sanitation Works Program for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 3.5699 | 160000000 | 1410000 | 0.8812% | 158590000
| TOTAL CAF | [5 empty] | 2166368000 | 1527681660.44 | 70.52% | 638686339.56
MOPC | Paved Road Rehabilitation and Maintenance Program - PAR 24 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 9 months | 42857143 | 36619928.88 | 85.45% | 6237214.12
MOPC | Enabling the Paved Road Network Program | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 0.95616 | 42750000 | 36695088.58 | 85.84% | 6054911.42
MOPC | Improvement and Paving Project for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-11 | 4.1178 | 354245764 | 58290405.52 | 16.45% | 295955358.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 3.3753 | 220000000 | 27744451 | 12.61% | 192255549
ANDE | Construction project for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-27 | 2.5781 | 45000000 | 0 | 0% | 45000000
| TOTAL FONPLATA | [5 empty] | 704852907 | 159349873.98 | 22.61% | 545503033.02
MAG | Project for Improved Family and Indigenous Production in Northeast Paraguay (PROMAFI) | 2016-10-06 | 6215 | 2018-10-31 | 2025-06-30 | 3 months | 8964000 | 8525805 | 95.1% | 438195
| TOTAL IFAD | [5 empty] | 8964000 | 8525805 | 95.1% | 438195
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 9 months | 21600000 | 21180854.87 | 98.06% | 419145.13
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 9 months | 10400000 | 4385267.83 | 42.17% | 6014732.17
| TOTAL OFID | [5 empty] | 32000000 | 25566122.7 | 79.89% | 6433877.3
ANDE | ANDE Transmission & Distribution System Upgrade (PHASE II) | 2017-12-06 | 6143 | 2018-08-07 | 2027-12-13 | 2.789 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL EIB | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5629584907 | 2847915695.3469 | 50.59% | 2781669211.6531
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
SENASA | Potable Water and Sanitation Program for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-19 | 6 months | 20000000 | 16056241.61 | 80.28% | 3943758.39
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 2029-04-24 | 4.1534 | 60000000 | 207510 | 0.3459% | 59792490
| TOTAL ICO | [5 empty] | 80000000 | 16263751.61 | 20.33% | 63736248.39
MOPC | Project for Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 4.2027 | 61053898.6224 | 0 | 0% | 61053898.6224
ANDE | Project for Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.5479 | 62150595.1585 | 36400370.4095 | 58.57% | 25750224.749
| TOTAL JICA | [5 empty] | 123204493.7809 | 36400370.4095 | 29.54% | 86804123.3715
ANDE | Construction Project of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2025-09-15 | 0.54521 | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0 | 75000000
ANDE | The High-Voltage Transmission System Expansion Project (Paraguay) | 2023-01-26 | 7414 | 2023-09-15 | 2029-01-26 | 3.9123 | 30000000 | 0 | 0% | 30000000
| TOTAL ICDF | [5 empty] | 30000000 | 0 | 0% | 30000000
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 308204493.7809 | 52664122.0195 | 17.09% | 255540371.7615
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 5937789400.7809 | 2900579817.3663 | 48.85% | 3037209583.4146
*Update of disbursements made from the year 2010 to 03/31/2025, according to SIGADE report 04/23/2025, 09:00 AM. - Exchange Rate: 03/31/2025 - Preliminary figures, subject to revision

## APRIL
EXTERNAL LOANS IN EXECUTION AS OF 04/30/2025
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant Program | 2019-04-05 | 6492 | 2020-01-02 | 2028-05-07 | 3.0219 | 125000000 | 31030658.3 | 24.82% | 93969341.7
MAG | Project to Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2026-05-25 | 1.0685 | 15000000 | 12879090.95 | 85.86% | 2120909.05
MEC | Project to Support Extended School Days and Improved Transportation Conditions for Students Attending Rural Official Schools | 2016-04-09 | 5961 | 2017-10-31 | 2025-06-10 | 2 months | 20000000 | 19323533.5 | 96.62% | 676466.5
MEF | Investments in Public Finances for Sustainable Development Project | 2019-04-05 | 6693 | 2021-01-14 | 2027-01-19 | 1.7233 | 25000000 | 13069362.59 | 52.28% | 11930637.41
MIC | Support for Business Development Services to Paraguayan Exporting Companies Program | 2017-07-18 | 6218 | 2018-11-19 | 2025-11-23 | 0.56712 | 10000000 | 10000000 | 100% | 0
MOPC | Rural Road Improvement Program II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0.71781 | 62000000 | 57264818.98 | 92.36% | 4735181.02
MOPC | Upgrade and Maintenance Project for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-20 | 5 months | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance Program | 2017-07-08 | 6236 | 2018-11-23 | 2025-11-30 | 0.5863 | 90000000 | 67124059.58 | 74.58% | 22875940.42
MOPC | Housing and Rehabilitation Program for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 2.5397 | 100000000 | 10782632.34 | 10.78% | 89217367.66
SENACSA | Project to Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 1.411 | 15000000 | 8062759.83 | 53.75% | 6937240.17
SENASA | Water and Sanitation System Construction Project for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2026-08-29 | 1.3315 | 40000000 | 34884660.34 | 87.21% | 5115339.66
MITIC | Digital Agenda Support Program | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 3.0247 | 130000000 | 38973629.44 | 29.98% | 91026370.56
MUVH | Improvement of Housing and Habitat Program | 2015-11-02 | 5665 | 2016-10-14 | 2025-10-20 | 6 months | 30000000 | 27347829.9 | 91.16% | 2652170.1
INE | Program to Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 1.6438 | 43000000 | 34712242.02 | 80.73% | 8287757.98
MOPC | Program to Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 2.6521 | 235000000 | 195198299.44 | 83.06% | 39801700.56
MOPC | Program to improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-03-16 | 3.8795 | 215000000 | 79284843.58 | 36.88% | 135715156.42
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay Program | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 2.3726 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 3.011 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 3.5699 | 30000000 | 8975310.13 | 29.92% | 21024689.87
MOPC | Potable Water and Sanitation Project for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 4.0356 | 115000000 | 0 | 0% | 115000000
MSPBS | Program to Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 3.9863 | 45000000 | 563598.16 | 1.252% | 44436401.84
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-25 | 3.9863 | 105000000 | 3093681 | 2.946% | 101906319
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector Program | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 3.1589 | 30000000 | 5015629 | 16.72% | 24984371
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions Project | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.3808 | 70000000 | 39741857.8 | 56.77% | 30258142.2
MOPC | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 4.9616 | 34050000 | 0 | 0% | 34050000
MSPBS | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 4.9616 | 25950000 | 0 | 0% | 25950000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3.7452 | 260000000 | 0 | 0% | 260000000
| TOTAL IADB | [5 empty] | 2070000000 | 860900716.95 | 41.59% | 1209099283.05
MAG | Market Access for Agricultural Products Project | 2020-04-14 | 6524 | 2020-03-26 | 2026-06-30 | 1.1671 | 100000000 | 60281406.37 | 60.28% | 39718593.63
MSPBS | Paraguay Public Health Sector Strengthening Program | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 1.1671 | 115000000 | 77952004.44 | 67.78% | 37047995.56
MOPC | Transport Connectivity Project – Habilitación de la Red Pavimentada | 2016-09-13 | 6025 | 2018-01-05 | 2025-12-31 | 0.67123 | 100000000 | 72668186.3 | 72.67% | 27331813.7
MOPC | Asuncion Riverfront Urban Resilience Project | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 3.6685 | 105000000 | 4552794.75 | 4.336% | 100447205.25
MOPC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2028-12-31 | 3.674 | 104190000 | 313250 | 0.3007% | 103876750
MEC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2028-12-31 | 3.674 | 21110000 | 0 | 0% | 21110000
| TOTAL IBRD | [5 empty] | 545300000 | 215767641.86 | 39.57% | 329532358.14
ANDE | Metropolitan Area Distribution System Improvement and National Interconnected System Reinforcement Project | 2017-01-20 | 6023 | 2018-01-05 | 2025-07-16 | 3 months | 150000000 | 148801129.81 | 99.2% | 1198870.19
ANDE | Improvement Project for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2026-06-12 | 1.1178 | 150000000 | 130921741.74 | 87.28% | 19078258.26
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening Program | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0.73425 | 170000000 | 157965758.61 | 92.92% | 12034241.39
MOPC | Rural Roads and Bridges Improvement Project in the Eastern Region | 2017-08-18 | 6237 | 2018-12-03 | 2025-06-05 | 2 months | 100000000 | 87251356.81 | 87.25% | 12748643.19
MOPC | Paved Road Rehabilitation and Maintenance Program - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 0.58356 | 100000000 | 80270580.95 | 80.27% | 19729419.05
MOPC | Integration Corridor Improvement and Road Reconstruction Program | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 2 months | 222076000 | 204850299.2 | 92.24% | 17225700.8
MOPC | Project for the development and maintenance of National Route No. 9 and access roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-19 | 5 months | 400000000 | 394388522.9 | 98.6% | 5611477.1
MOPC | Enabling the Paved Road Network Program | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | 1.7151 | 100000000 | 92706138.98 | 92.71% | 7293861.02
MOPC | Project for the Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 0.65205 | 212000000 | 122903390.33 | 57.97% | 89096609.67
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization Program of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-17 | 1.6329 | 250000000 | 93431179.85 | 37.37% | 156568820.15
MOPC | Construction Project for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2030-04-05 | 4.9342 | 100000000 | 25926252.19 | 25.93% | 74073747.81
MOPC | Sanitation in Intermediate Cities Program | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 3.1973 | 52292000 | 5802379.22 | 11.1% | 46489620.78
MOPC | Sanitation Works Program for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 3.4877 | 160000000 | 1574442.25 | 0.984% | 158425557.75
| TOTAL CAF | [5 empty] | 2166368000 | 1546793172.84 | 71.4% | 619574827.16
MOPC | Paved Road Rehabilitation and Maintenance Program - PAR 24 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 8 months | 42857143 | 36619928.88 | 85.45% | 6237214.12
MOPC | Enabling the Paved Road Network Program | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 0.78904 | 42750000 | 36695088.58 | 85.84% | 6054911.42
MOPC | Improvement and Paving Project for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-11 | 3.9507 | 354245764 | 58290405.52 | 16.45% | 295955358.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 3.2082 | 220000000 | 27744451 | 12.61% | 192255549
ANDE | Construction project for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-27 | 2.411 | 45000000 | 35000 | 0.07778% | 44965000
| TOTAL FONPLATA | [5 empty] | 704852907 | 159384873.98 | 22.61% | 545468033.02
MAG | Project for Improved Family and Indigenous Production in Northeast Paraguay (PROMAFI) | 2016-10-06 | 6215 | 2018-10-31 | 2025-06-30 | 2 months | 9427140 | 8525804.6369 | 90.44% | 901335.3631
| TOTAL IFAD | [5 empty] | 9427140 | 8525804.6369 | 90.44% | 901335.3631
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 8 months | 21600000 | 21180854.87 | 98.06% | 419145.13
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 8 months | 10400000 | 4385267.83 | 42.17% | 6014732.17
| TOTAL OFID | [5 empty] | 32000000 | 25566122.7 | 79.89% | 6433877.3
ANDE | ANDE Transmission & Distribution System Upgrade (PHASE II) | 2017-12-06 | 6143 | 2018-08-07 | 2027-12-13 | 2.789 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL EIB | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5621948047 | 2877700868.5369 | 51.19% | 2744247178.4631
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
SENASA | Potable Water and Sanitation Program for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-19 | 4 months | 20000000 | 19056241.61 | 95.28% | 943758.39
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 2029-04-24 | 3.9863 | 60000000 | 207510 | 0.3459% | 59792490
| TOTAL ICO | [5 empty] | 80000000 | 19263751.61 | 24.08% | 60736248.39
MOPC | Project for Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 4.2027 | 63971412.5561 | 0 | 0% | 63971412.5561
ANDE | Project for Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.5479 | 65120515.6951 | 36686368.581 | 56.34% | 28434147.1141
| TOTAL JICA | [5 empty] | 129091928.2511 | 36686368.581 | 28.42% | 92405559.6701
ANDE | Construction Project of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2025-09-15 | 5 months | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0 | 75000000
ANDE | The High-Voltage Transmission System Expansion Project (Paraguay) | 2023-01-26 | 7414 | 2023-09-15 | 2029-01-26 | 3.9123 | 30000000 | 0 | 0% | 30000000
| TOTAL ICDF | [5 empty] | 30000000 | 0 | 0% | 30000000
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 314091928.2511 | 55950120.191 | 17.81% | 258141808.0601
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 5936039975.2511 | 2933650988.7279 | 49.42% | 3002388986.5233
*Update of disbursements made from the year 2010 to 04/30/2025, according to SIGADE report 05/22/2025, 09:00 AM. - Exchange Rate: 04/30/2025 - Preliminary figures, subject to revision

## MAY
EXTERNAL LOANS IN EXECUTION AS OF 05/31/2025
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant Program | 2019-04-05 | 6492 | 2020-01-02 | 2028-05-07 | 2.937 | 125000000 | 31030658.3 | 24.82% | 93969341.7
MAG | Project to Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2026-05-25 | 0.98356 | 15000000 | 12879090.95 | 85.86% | 2120909.05
MEC | Project to Support Extended School Days and Improved Transportation Conditions for Students Attending Rural Official Schools | 2016-04-09 | 5961 | 2017-10-31 | 2025-06-10 | 1 month | 20000000 | 19323533.5 | 96.62% | 676466.5
MEF | Investments in Public Finances for Sustainable Development Project | 2019-04-05 | 6693 | 2021-01-14 | 2027-01-19 | 1.6384 | 25000000 | 13069362.59 | 52.28% | 11930637.41
MOPC | Rural Road Improvement Program II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0.63288 | 62000000 | 57264818.98 | 92.36% | 4735181.02
MOPC | Upgrade and Maintenance Project for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-20 | 4 months | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance Program | 2017-07-08 | 6236 | 2018-11-23 | 2025-11-30 | 6 months | 90000000 | 67124059.58 | 74.58% | 22875940.42
MOPC | Housing and Rehabilitation Program for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 2.4548 | 100000000 | 10782632.34 | 10.78% | 89217367.66
SENACSA | Project to Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 1.326 | 15000000 | 8062759.83 | 53.75% | 6937240.17
SENASA | Water and Sanitation System Construction Project for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2026-08-29 | 1.2466 | 40000000 | 37000000 | 92.5% | 3000000
MITIC | Digital Agenda Support Program | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 2.9397 | 130000000 | 38973629.44 | 29.98% | 91026370.56
MUVH | Improvement of Housing and Habitat Program | 2015-11-02 | 5665 | 2016-10-14 | 2025-10-20 | 5 months | 30000000 | 27347829.9 | 91.16% | 2652170.1
INE | Program to Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 1.5589 | 43000000 | 34712242.02 | 80.73% | 8287757.98
MOPC | Program to Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 2.5671 | 235000000 | 195198299.44 | 83.06% | 39801700.56
MOPC | Program to improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-03-16 | 3.7945 | 215000000 | 79284843.58 | 36.88% | 135715156.42
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay Program | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 2.2877 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 2.926 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 3.4849 | 30000000 | 8975310.13 | 29.92% | 21024689.87
MOPC | Potable Water and Sanitation Project for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 3.9507 | 115000000 | 0 | 0% | 115000000
MSPBS | Program to Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 3.9014 | 45000000 | 563598.16 | 1.252% | 44436401.84
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-25 | 3.9041 | 105000000 | 3093681 | 2.946% | 101906319
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector Program | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 3.074 | 30000000 | 5015629 | 16.72% | 24984371
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions Project | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.2959 | 70000000 | 39741857.8 | 56.77% | 30258142.2
MOPC | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 4.8767 | 34050000 | 0 | 0% | 34050000
MSPBS | Strengthening of the San Estanislao Hospital Services Network Program | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 4.8767 | 25950000 | 0 | 0% | 25950000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3.6603 | 260000000 | 0 | 0% | 260000000
| TOTAL IADB | [5 empty] | 2060000000 | 853016056.61 | 41.41% | 1206983943.39
MAG | Market Access for Agricultural Products Project | 2020-04-14 | 6524 | 2020-03-26 | 2026-06-30 | 1.0822 | 100000000 | 60281406.37 | 60.28% | 39718593.63
MSPBS | Paraguay Public Health Sector Strengthening Program | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 1.0822 | 115000000 | 77952004.44 | 67.78% | 37047995.56
MOPC | Transport Connectivity Project – Habilitación de la Red Pavimentada | 2016-09-13 | 6025 | 2018-01-05 | 2025-12-31 | 7 months | 100000000 | 72668186.3 | 72.67% | 27331813.7
MOPC | Asuncion Riverfront Urban Resilience Project | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 3.5836 | 105000000 | 4552794.75 | 4.336% | 100447205.25
MOPC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2028-12-31 | 3.589 | 104190000 | 313250 | 0.3007% | 103876750
MEC | Joining Efforts for an Education of Excellence in Paraguay Project | 2024-08-07 | 7433 | 2025-01-07 | 2028-12-31 | 3.589 | 21110000 | 0 | 0% | 21110000
| TOTAL IBRD | [5 empty] | 545300000 | 215767641.86 | 39.57% | 329532358.14
ANDE | Metropolitan Area Distribution System Improvement and National Interconnected System Reinforcement Project | 2017-01-20 | 6023 | 2018-01-05 | 2025-07-16 | 2 months | 150000000 | 148801129.81 | 99.2% | 1198870.19
ANDE | Improvement Project for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2026-06-12 | 1.0329 | 150000000 | 130921741.74 | 87.28% | 19078258.26
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening Program | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0.64932 | 170000000 | 157965758.61 | 92.92% | 12034241.39
MOPC | Rural Roads and Bridges Improvement Project in the Eastern Region | 2017-08-18 | 6237 | 2018-12-03 | 2025-06-05 | 1 months | 100000000 | 87251356.81 | 87.25% | 12748643.19
MOPC | Paved Road Rehabilitation and Maintenance Program - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 6 months | 100000000 | 80270580.95 | 80.27% | 19729419.05
MOPC | Integration Corridor Improvement and Road Reconstruction Program | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 1 months | 222076000 | 204850299.2 | 92.24% | 17225700.8
MOPC | Project for the development and maintenance of National Route No. 9 and access roads | 2018-05-04 | 6151 | 2018-09-18 | 2025-09-19 | 4 months | 400000000 | 394388522.9 | 98.6% | 5611477.1
MOPC | Enabling the Paved Road Network Program | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | 1.6301 | 100000000 | 92706138.98 | 92.71% | 7293861.02
MOPC | Project for the Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 7 months | 212000000 | 122903390.33 | 57.97% | 89096609.67
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization Program of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-17 | 1.5479 | 250000000 | 93431179.85 | 37.37% | 156568820.15
MOPC | Construction Project for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2030-04-05 | 4.8493 | 100000000 | 25926252.19 | 25.93% | 74073747.81
MOPC | Sanitation in Intermediate Cities Program | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 3.1123 | 52292000 | 5802379.22 | 11.1% | 46489620.78
MOPC | Sanitation Works Program for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 3.4027 | 160000000 | 1574442.25 | 0.984% | 158425557.75
| TOTAL CAF | [5 empty] | 2166368000 | 1546793172.84 | 71.4% | 619574827.16
MOPC | Paved Road Rehabilitation and Maintenance Program - PAR 24 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 7 months | 42857143 | 36619928.88 | 85.45% | 6237214.12
MOPC | Enabling the Paved Road Network Program | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 0.70411 | 42750000 | 36695088.58 | 85.84% | 6054911.42
MOPC | Improvement and Paving Project for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-11 | 3.8658 | 354245764 | 58290405.52 | 16.45% | 295955358.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 3.1233 | 220000000 | 31290071 | 14.22% | 188709929
ANDE | Construction project for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-27 | 2.326 | 45000000 | 35000 | 0.07778% | 44965000
| TOTAL FONPLATA | [5 empty] | 704852907 | 162930493.98 | 23.12% | 541922413.02
MAG | Project for Improved Family and Indigenous Production in Northeast Paraguay (PROMAFI) | 2016-10-06 | 6215 | 2018-10-31 | 2025-06-30 | 1 months | 9418840 | 8241592.1997 | 87.5% | 1177247.8003
| TOTAL IFAD | [5 empty] | 9418840 | 8241592.1997 | 87.5% | 1177247.8003
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 7 months | 21600000 | 21180854.87 | 98.06% | 419145.13
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement Project | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 7 months | 10400000 | 4385267.83 | 42.17% | 6014732.17
| TOTAL OFID | [5 empty] | 32000000 | 25566122.7 | 79.89% | 6433877.3
ANDE | ANDE Transmission & Distribution System Upgrade (PHASE II) | 2017-12-11 | 6143 | 2018-08-07 | 2027-12-13 | 2.789 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL EIB | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5611939747 | 2873077615.7597 | 51.2% | 2738862131.2403
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
SENASA | Potable Water and Sanitation Program for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2025-08-19 | 3 months | 20000000 | 19056241.61 | 95.28% | 943758.39
MOPC | Water and Sanitation Program for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 2029-04-24 | 3.9014 | 60000000 | 207510 | 0.3459% | 59792490
| TOTAL ICO | [5 empty] | 80000000 | 19263751.61 | 24.08% | 60736248.39
MOPC | Project for Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 3.9507 | 63279733.8508 | 0 | 0% | 63279733.8508
ANDE | Project for Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 4.2959 | 64416412.5312 | 57579164.4038 | 89.39% | 6837248.1274
| TOTAL JICA | [5 empty] | 127696146.382 | 57579164.4038 | 45.09% | 70116981.9782
ANDE | Construction Project of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2025-09-15 | 4 months | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0 | 75000000
ANDE | The High-Voltage Transmission System Expansion Project (Paraguay) | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3.6603 | 30000000 | 0 | 0% | 30000000
| TOTAL ICDF | [5 empty] | 30000000 | 0 | 0% | 30000000
MDN | Project for the Procurement of Aerial Platforms (Aircraft) with Advanced Technological Capabilities for the Defense of National Airspace and Support in Counter-Narcoterrorism Operations | 2024-11-19 | 7479 | 2025-05-30 | 2028-07-01 | 3.0877 | 101606009 | 0 | 0% | 101606009
| TOTAL BNDES | [5 empty] | 101606009 | 0 | 0% | 101606009
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 414302155.382 | 76842916.0138 | 18.55% | 337459239.3682
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 6026241902.382 | 2949920531.7734 | 48.95% | 3076321370.6086
*Update of disbursements made from the year 2010 to 05/31/2025, according to SIGADE report 06/25/2025, 09:00 AM. - Exchange Rate: 05/30/2025 - Preliminary figures, subject to revision